## Must-Do
Must-Do Work to Prepare for the End of the Raiser's Edge Database View
Database View End Date: September 15, 2027
Our Internal Deadline: August 15, 2027
Focus: Tasks still done in the database view
Gray rows are projects/events with immovable dates, white rows are tasks to be completed any time before Internal deadline.
Hint: Enter the task/projects with the primary task worded first so this column can be sorted by topic if desired
Start Date | Due Date | Date Completed | Responsible | User Affected | Task/Project | Notes
|  |  |  | Beth | Recurring Gift charging from db view to web view | Move as soon as we have time
| 2026-10-31 |  | Beth | Beth | Daily batch entry to web view | Been waiting for Batch parity
|  |  |  | Beth | Stock gift entry to web view
|  |  |  | Beth | Address updates to web view | Waiting for constituent record layout re-do
|  |  |  | Beth | Ack export from db view to web view | Waiting for Acks to appear in web view
|  |  |  | Tyrone | Newsletter from Quick Letters in db view to QL in web view | Waiting for QL to appear in web view
|  |  |  | Tyrone | Annual report reports to web view | Move asap, export for printer is better in web view than db view
2026-11-23 | 2027-01-15 |  | End of Year Gift Processing is the Focus
2027-05-17 | 2027-05-21 |  | Graduation Week: all hands on deck
2027-07-01 | 2027-07-31 |  | Nyiema | Nyiema | Import of new students and parents, roll over of graduating students and parents
2027-07-05 | 2027-07-16 |  | Tyrone | Tyrone | Tyrone out on vacation
2027-07-15 | 2027-08-01 |  | Tyrone | Tyrone | If web view AddressFinder hasn't improved and been moved to web view yet, we're forced to do it in web view, get it set up | Looking for (1) more control over timing and (2) more control over format

## Could-Do
Could-Do Tasks and Projects to Make the Most of Raiser's Edge NXT
Focus 1: Improvements we can make in the use of the web view
Focus 2: Improvements we can make in the use of RE NXT in either view
Focus 3: Other RE projects (cleanup, documentation, new tools, process improvements, etc.)
Priority | Responsible | Task/Project | Notes
AI: Implement RE NXT AI
|  | Consent to work with our Solicit Codes | https://community.blackbaud.com/discussion/86397/beyond-solicit-codes-building-a-modern-communication-preference-strategy-with-consent
High |  | Work Center Training for Fundraisers